## Grid 1 Site Manager (EN)
IO1-A3a - Grid 1: Professional Activities and Associated Skills & Knowledge for Building Renovation Site Managers
|  | Ability to analyze, evaluate problems, project, anticipate and adapt to complex situations, also taking into account the co-activity on site. | Internal communication skills on site and within the company, including finding alternative solutions in complex situations. Ability to use appropriate communication tools to manage teams. | Ability to manage formal contacts and communication with external partners (customers, subcontractors, suppliers, etc.). Ability to use appropriate communication and monitoring tools. | Ability to mentally manage workload, including managing stress and work tensions. Management and personnel management | Ability to use computer tools to analyze, evaluate and anticipate. | Knowledge to plan, implement and control the quality of production processes in renovation sites, including legal aspects, human resources management, organization and control of supplies. --- Knowledge to plan and control the quality of intermediate and final productions. |  | Knowledge to master the financial stakes and the budget allocated to the renovation site. | Knowledge of how to integrate the energy standards of buildings during their renovation and to use the appropriate control tools. | Knowledge to integrate the circular economy on renovation sites and to use the appropriate control tools. | Knowledge to integrate health and safety at work prevention in renovation sites and to use the appropriate control tools.
Phase 1: Preparation of a renovation site (the emphasis should be on this type of site): this work is absolutely essential for the progress of the renovation site (site = it is a fight that is prepared) RESPONSIBILITY: 50/50 with the works manager; 100% responsibility on small sites * The site manager is more in the coordination of the different tasks. He is devolved to the operational and responsible for safety * he is responsible for anticipating situations following the analysis of plans and situations observed (exploitation of the information they contain) * he/she is responsible for the preparation of his/her internal and external communication plan AUTONOMY: * the preparation of the site is done in binomial with the works manager, in consultation with the company manager, the client and his representative (often the architect) * in small companies, the autonomy of the site manager is almost total
Activity 1.1. Renovation Site Analysis | Responsibilities * It is the site manager who decides what can and cannot be done in relation to the normative references on a renovation site, by playing the balance between what is allowed or not. * He is responsible for reconciling the renovation project with the local urban plan (PLU) * It gives an initial opinion on the documents. He also warns about possible difficulties, defects or malfunctions that could occur during the renovation work. Tasks * Be aware of the written documents, be able to highlight the essential things by having a critical look at the documents available (general requirements) * Prepare the operating procedure and the arguments for his team allowing its implementation (first version); operating procedures that are specific and not standardized on renovation sites * Analysis of written documents, are there gas pipes, architect's plans, technical documents, etc. (in renovation, the building exists, so it is easier to have written documentation concerning it): technical and particular clauses (CCTP), architect's plan, declaration of intention and commencement of work (DICT), etc. | Specificity: the adaptation to the existing which characterizes renovation and diagnosis. * It is more complicated in renovation, it is necessary to foresee much more things (how to make pass a crane, arrival of the water points, how I evacuate the dumpsters, the rubble, which is the width of the access road, etc., availability of the electric cables, upstream of the visit of the building site) - feasibility study * To have a precise vision of what is on site, lot by lot, e.g. what is the coating of the installations * A great ability to adapt when you are a site manager (you don't know what you will find) * It must think about the realization of the works and their feasibility and all the surrounding. The accesses, the available space, the available height. * Knowing how to read and analyse written material, identifying delicate points (tensions, difficulties, risks) * Be able to make your own roadmap to analyze a renovation site (anticipate difficulties) - prepare them for routines * Have the ability to anticipate insofar as you have to prepare your planning from A to Z (know how to materialize your table) | * Site installation plan - also a communication document (available to all participants on site) * Another dynamic Autocad document, - a tool to manage co-activity on site * Alert on the critical points: the site manager must communicate during the first meeting of the site the elements concerning each future participant. | * Knowing how to show the client how the building will become (knowing how to distinguish between technical documents and communication documents) - creating evolutionary documents for dialogue, transmission and communication. The most important thing for the site manager is to feel and sense the wish and desire of the client, the project. • To feel the customer's need (the clientele is very specific and very heterogeneous) - the building, it carries values and it carries human activities, not betray the client's wishes, explain the constraints that limit their wishes • Know the specificity of external partners (all concessionaires, utilities, EDF, (e.g. roads, etc.) - to have permanent contacts | Be organized (have a good command of documents, know how to adapt them to your own functioning) * Big concern: recruitment and management of personnel on site, especially if there is a shortage of manpower. * Establish support groups of team leaders. * Learn to consider the unexpected as a sustainable component * Have a balanced professional life Consider internships with work psychologists who would analyze stressful work situations Women would make better site managers because they are better able to handle the unexpected and the mental load, they are able to manage emotions, they find solutions more easily in difficult situations. | * Knowing how to read plans, analysis of graphical parts, architectural plans, structural plans * BIM in renovation to prepare the building site, this allows to model the works (e.g. simulate openings, etc.) - create models * Master Autocad * Knowledge of Excel (at least) - Gantt chart * BIM for digital mock-ups * Improve written expression * Read incoming computer documents | * Perfect knowledge of the documents relating to the renovation of a building, knowledge of the site a perfect conniassance of all the initial documents. * To be able to build one's own roadmap for the observation of the construction site, with all its components (a support from which the expertise will emerge later) * Site visit: tool for anticipating achievements (more complex for renovation): foresee demolitions, replacements, hidden defects, etc. * Digging into the "reading of the plans": it is more the analysis of the plans to organize the tasks to be done, to anticipate the problems, decoding (analysis and decoding of the plans in order to ...) - know how to exploit the information contained in the plans. • Matching the technical possibilities of a renovation project with the available budget and the needs/wishes of the clients | * Find compromises between constraints (including security) and expected achievements * Knowing how to select teams with the right skills for the tasks at hand. * The site manager recruits his workforce: he determines the quality and quantity of workers needed | * Understand the estimate, understand the financial cuts (know what has been cut) - the financial part is more the responsibility of the site manager, on smaller sites, the site manager makes direct purchases, the site manager has a budget to manage (purchase orders), then refer to the site manager • Define its program and its funding envelope | * To know the regulations relating to the energy standards of buildings during their renovation and to use the appropriate control tools. | * To know the regulations to integrate the circular economy on renovation sites and to use the appropriate control tools. | * To know the regulations for integrating health and safety at work prevention in renovation sites and to use the appropriate control tools. * consult the security document
Activity 1.2. Site visit of the future renovation site | Responsibilities * Responsibility for feasibility checks: the building to be renovated already exists, it is up to us to adapt to the building, and not the other way around (big difference with new construction) * Global apprehension of the site: identify the co-activity, the supply, prepare the formalization of the routine on site, by thinking spontaneously about the essential things which will take place there. Tasks * Identify situations where you will need to adapt to reality as it is (e.g. where to break, when and how) * Identify potential difficulties and peculiarities (e.g. where it will be difficult to meet all the standards, what solutions to find) * Understand the context, understand it, analyse the access, the neighbourhood, the connections, etc. * Identify the supply and storage areas and the conditions for applying safety rules * Formalization of the site installation plan (especially on large renovation sites, not always on small or simple sites)
Activity 1.3. Diagnosis of the existing building prior to intervention | Responsibilities * Identify the conditions of his intervention (responsibility for a thorough technical visit to understand his intervention and organize the work) * Taking into account financial risks * Propose solutions (renovation is a permanent search for solutions) - e.g. old premises next to another particular building, do not touch it * Paying attention to all aspects of technical feasibility, in connection with the technical knowledge of the structure and the supports of the building to be renovated, knowing the supports. Tasks * Formalize observations, analyze constraints in a distanced way (how to deal with the identified constraints), as the technical right-hand man of the company manager * Communicate this diagnosis to the team leaders, explain to them how to respect the old while respecting the current standards * Describe the tasks to be performed, including thermal break points, for example, highlighting all important elements, * Consult with the design office (the site manager provides the design office with information so that it can make an appropriate diagnosis) * Carry out "destructive surveys" to identify infestations, invisible damage, asbestos problems, hidden lead, etc., to better anticipate the future.
Activity 1.4. Preparation of the renovation site plan and its layout (tracing, fencing and preparation of the site area) | Responsibilities * Design the organization and layout plans for the renovation site, and communicate them to the team leaders. Tasks * Finalize the description of the tasks to be carried out, taking into account the realities and constraints (e.g. thermal breaks to be managed) which will condition the complexity of the renovation site. * Explain constraints to team leaders (e.g. how to pass beams) * Contact the municipal services to neutralize the access road, private transport, etc.
Activity 1.5. Planning and phases of the team's work | Responsibilities * Identify and anticipate the roles of different stakeholders and the tasks they will be responsible for. * Manage the authorizations for the use of the road and public spaces in general allowing access to the construction site. Tasks * Plan the initial inventory of fixtures, which is very important for the subsequent acceptance of the building site (note all visible damage or apparent defects to protect yourself from potential disputes at the end of the construction period). construction site) * Establish the rotation plans of the teams on the renovation site (own teams and subcontractors). * Define co-activities (co-activity is planned well in advance) - very important in relation to planning to quantify the tasks in the renovation. * Explain well to the client what will happen between the starting point and the end point, especially in terms of the constraints of the project: this is particularly important if the renovation site remains inhabited ("clients want results, but not work"). * Requesting 5% of the budget in supply of unforeseen costs
Phase 2: Managing the activities of a renovation site RESPONSIBILITY: 100% operational responsibility, especially if the sites are small, by organizing the co-responsibilities of the other parties involved (health and safety coordinator, project owner and project manager). * the site manager is the first guarantor of what happens on the site: guarantor of safety, quality and proper functioning of the renovation sites (non-standard by definition - with evouative specifications depending on the situation) * he is responsible for anticipating situations during the execution of the work (particularly complex task on renovation sites) * is responsible for the execution of its internal and external communication plan * he is responsible for the sequence of the different sequences (activities): he manages all the logistics, it is not more complicated than new construction, but it is different, because it is necessary to respect the existing building AUTONOMY: maximum at the operational level REPORTING to his hierarchy
Activity 2.1. Team briefing / debriefing (daily and periodic) | Responsibilities * Organize briefings with his team leaders to review what was done the day before and what will be done during the day. Tasks * Analyze what was done yesterday and what needs to be done today (with team leaders, sometimes clients, design offices) * Emphasize what needs to be anticipated, detect upcoming delicate moments, avoid tensions * Identify the cost of non-anticipation (delays, additional financial costs, supply difficulties, misunderstanding on the part of the customer, etc.) | Working on common sense: giving meaning to procedures. Three things: human issues (the guy has to feel good on the site), safety including securing my own responsibility, societal issues. It has to be credible. The site manager commands the work. The foreman will be closer to the workers, while the site manager coordinates the foremen. He is more in touch with the team leaders. • A particular professional posture: one cannot start from a technological scheme learned in class, one needs flair and experience to choose the right courses of action * Power to act in unpredictable situations, to manage the unexpected. * He manages the hours, the quantities, while the The work manager translates it into €. • You have to be very careful. * Knowing how to activate the technical skills of the site manager (use of plans, respect of procedures, topography skills) Beware, the site manager cannot be technically competent in all trades. Only the experience can bring the necessary knowledge. Generally speaking, the knowledge linked to the structure or to the existing building is primordial, it is an important prerequisite. Key words: listening and understanding, empathy, negotiation, solidarity with the customer * Knowing how to manage construction sites when the inhabitants are there (e.g. housing rehabilitation) | * Disseminate the right information to the team * Get into the habit of communicating in co-activity, with teams, with customers. the site manager must be able to argue with the project owner to finance unforeseen events (and upstream to set aside the necessary negotiation funds) * On small sites, the two functions are merged. He will be called "team leader". You can't become a foreman without experience. You need knowledge, but above all experience. He is above all a manager. * Know how to communicate rotation plans to other trades * Know how to communicate with people on site (colour codes, languages, etc.) • Transmit messages to teams, transmit instructions, choose the right means, make sure they understand; give instructions that are understood by everyone, keep communication simple, know how to decode and construct your message, retransmit; make sure the message is correct understanding of instructions (1/4 h safety). • We must be vigilant with regard to skills Technical skills of the teams: the site manager must be vigilant in monitoring his technical skills (use of plans, topographic tools, understanding of the functioning of the different trades and the interactions that are created between them). Learning technical skills, starting with the structural work (very important in renovation). This is an important prerequisite. * the difference is the discussion with the customer, because with the old building the customer has an emotional relationship (IMPORTANT) - dealing with assimetic volumes, arytmies, etc. * The client should not feel that the team is not cohesive. | We do 360°: in relation with everyone, with all the participants. In renovation, the client's presence will be more frequent. The presence of safety coordinators will be more frequent. * The more outward looking we get, the more difficult communication can be. * Commercial dimension of the site manager and advice. Site managers are involved in customer relations: reassuring them, explaining the progress of the site, and doing a bit of sales. * The management of occupants in an occupied site is a very important point. Relational skills are essential. There is a very specific professional knowledge which must be impelled and managed by the site manager * Relationship with architect, CSPS coordinator and others ... diplomacy, mediation. The experience is a very good school! * The site manager must be able to measure or evaluate the risks or opportunities (technical, financial) to know if he can take them without harming the quality of the site. It is part of his prerogatives. But it is not written anywhere ... * He reports problems to the architect encountered on the site . * The management of the occupants of a building site is a specific capacity for renovation sites. Depending on the person you are talking to, the topics of safety, technology, programming or quality will be discussed. Important reporting. We are more in a customer relationship and reporting. Relational with the customer (reassure, inform, take into account the fears of the customer). To have a permanent "commercial" discourse. The site manager is the interface between very different interlocutors (customer, workers, team leaders, customer, various authorities (work inspection, gendarmerie, CSPS health and safety coordinator) etc? * knowing how to communicate with the client in a more nuanced way, convincing him to find solutions that cannot be based solely on emotions linked to an old building to which he is attached, etc. * to have a good posture, a particular professional knowledge with the customer, not to find the door closed | Think about the bailiff's report to be made in order not to endorse possible damages already existing in the neighborhood and which could be imputed to the realization of the building site. Hyper solicitation requires a life balanced. The most difficult thing: projecting yourself in a realistic way is a source of stress Anticipating hazards in renovation Fear of criminal law, risk management (human, economic, societal) responsible for recruiting personnel, including interim, leading teams: getting them to come to work every day, having guys in the right position; we rely on their dialogue skills, we present the workstation, we welcome them - the welcome is a test to see if the guy is suitable (know how to welcome the newcomer, on a fixed-term or permanent contract), know how to measure the skills of newcomers on a site - the site manager welcomes the company (welcome sheet, this allows us to check a lot of things) | * Knowing how to read plans, analysis of graphical parts, architectural plans, structural plans * BIM in renovation to manage the building site, this allows to model the works (e.g. simulate openings, etc.) - create models * Master Autocad * Knowledge of Excel (at least) - Gantt chart * BIM for digital mock-ups * Improve written expression * Read computer documents | * Compatibility between existing and new materials must be taken into account Beware of the phenomenon of the semi-bearing wall (initial partition which over time becomes a bearing or stabilising element in the building) In training it is necessary to train to this approach of "surprise" to solve. • Control of the works (including The inspector is responsible for the quality of the work (e.g. self-checking, on his own initiative), based on the plans. He repeats the controls by sampling, during the works. There can be self-checking sheets (designed either by works managers or by site managers). | * Building permit or declaration of works (legislative aspects) * PSMV (plan de sauvegarde et de mise en valeur) to be consulted and any other regulation in relation to classified or unclassified heritage sites. | Specific regulations in terms of energy impact (RT 2020 etc ...) Specific VAT, premiums and subsidies to advise the owner | * Knowledge of what is deductible from L10taxes, interest-free loans (the site manager has an obligation to advise, participate in commercial negotiations - the various tax reductions that can encourage customers to renovate) * Know the limits (what can be renovated and what cannot be renovated), listed buildings, streets not to be touched, local renovation standards | * The site manager must have an updated and complete knowledge allowing to identify the various wastes and to know the processes of storage and treatment or reprocessing. * Know how to deal with non-routine waste, asbestos, etc. * Waste sorting and energy saving (e.g. water fountains) - again, a matter of communication with the teams; skips are a cost. | * How to conciliate preservation and integrity of the existing while respecting the safety regulations (drilling in the joints and not in the stone); the safety net etc... These are more adaptations to find than compromises. The site manager must take a very specific approach to this type of situation. * Enforce compliance with safety regulations, don't just talk about safety in terms of costs. It is also an investment. A change in mentality is necessary. Show the benefits in concrete terms. Build communication tools to convey safety messages: activity-risk ratio. Activity 2.2. Development and implementation of procedures for the proper execution of operations (e.g. adaptation to site constraints, verification and monitoring of material supplies, verification of delivery times, consideration of energy efficiency, etc.) Responsibilities * The team leader warns and the site manager finds solutions (e.g. an apparently healthy wall turns out to be rotten when opened: what to do, especially when the surface is large?) * Manage day-to-day contact with clients (it is important to explain to the client what each change to the original plan entails). Tasks * Maintain a more personal relationship with the customer, taking into account his sensitivities, his constraints and his emotional side (the site manager is the privileged interlocutor of the customer) to remain credible and legitimated in front of the customer (crucial aspect for the good progress of a renovation site) * Adapt to site constraints by organizing team activities. * Follow up on the daily supply of materials and ensure that delivery deadlines are met. * Take into account energy efficiency, circular economy, health and safety on site in the balancing and communication of procedures. * Provide for budgetary adjustment possibilities Activity 2.3. Management of teams on renovation sites (own teams, in cooperation, subcontractors, etc.): monitoring of tasks and anticipation of complex and conflictual situations. Management and monitoring of the teams' work process, including monitoring and updating of the work schedule, co-activity on site, etc. Responsibility This activity is the most sensitive: as soon as you get involved with people, it's complex (you have to choose your team leaders well, to get along with them): * Adopt the posture of manager (absolutely fundamental responsibility during this key activity), by controlling the organization of the site. * To avoid the bad management of the renovation site (the slippages are much easier than on the new sites) to avoid conflicts (open or latent within the teams of which the customers can be aware and which harm in the long run the site and the company). * The site manager has the power to "plant" the site, especially if he is not present on the site. Tasks * Recruiting your teams. * Organize the increasingly complex co-activity. * Convey relevant messages to teams (instructions and explanations), paying attention to language and map reading barriers to adapt to varied and diverse audiences. * Carefully craft messages for clients, taking into account their diversity and sensitivity, by activating communication skills. * Informing the teams about safety prevention and passing on instructions to respect the rules, by activating its communication skills and using media adapted to the specificities of renovation sites. * Give the teams the necessary means to carry out what is required. Explain why the means are sometimes lacking, even if the work must be done in spite of everything. * Being often on the ground - this is imperative for renovation sites, the team must feel that he is present, in support of the team leaders who cannot do everything, so he must be present to assist the teams, be able to protect them if necessary, and stand by them in front of the client. * Organize the different interventions well (e.g. the one who has the crane, has the power). Activity 2.4. Follow-up of relations with the client, the project manager, the architect, the design office, the CSPS (health and safety coordinator). Responsibilities * Adjust the organization of the site and the achievements to the constraints of renovation which one discovers as one goes along (including supplies, subcontracting, etc.), by negotiating with the appropriate interlocutors. * Measure the risk, be tough if you have to (especially important when dealing with safety - if workers don't want to put up a scaffold to save half a day, be assertive about not making them work on a ladder where a scaffold is needed). * Adapting the posture and the discourse to each interlocutor (one adapts a different discourse and a different attitude with an architect (the exchanges are more technical and descending with the architect, there are no relational/motivational stakes, one adapts a posture of the one who is accountable, whereas with the worker, one is a manager). Tasks * Managing surprises and convincing your interlocutors to accept changes within the budget, making them understand that not everything can be planned in advance (e.g. pipes to be adjusted, resizing of foundations, etc.) * Negotiate with partners outside the hierarchy (this is learned in an empirical way, so not learning the law or the rule, but its concrete application in a situation on site, the examples are taken from experience on site, based on these abilities of being a graduate) * Managing complex relationships with architects, especially when it is necessary to negotiate adjustments imposed by the complexity of renovation projects, which are by definition atypical (there must be a partnership with the architect). Activity 2.5. Organization and control of on-site protection, including assembly/disassembly of scaffolding, work at height, difficult access, use of dangerous products on renovation sites, etc. Responsibilities Knowing how to make trade-offs: taking into account the cost of different solutions, safety issues, knowing how to measure and assume the risks, in consultation with the team (Safety guides the choice: if several choices are possible, it is the cost factor that will determine the choice). * To know the legislation related to the rules of protection, safety and health, to know the procedures to follow * Identify different types of risks, such as chemical risks * Identify means of access and circulation * Impose choices and trade-offs Tasks * Regular site visits to keep track of the entire renovation project. * Negotiate and use situational intelligence to avoid being a prisoner of norms, while respecting them. * Impose safety, while respecting the existing building ("in the new building, there are habits that cannot be applied in the renovation") * Finding non-standard solutions for non-standard work situations, e.g. finding special scaffolding, mobile cranes, narrow excavators, etc. These solutions have an additional cost, you have to anticipate (performance with experience). Activity 2.6. Management of waste treatment in renovation sites: planning and management of waste bins, sorting and recycling operations. Responsibilities * The site manager must be able to treat ALL types of waste including unforeseen ones such as asbestos, lead or other (regulations and treatment techniques to be known and respected) * The site manager is responsible for setting up the skips, supplies, various evacuations and the protections to be implemented. Tasks * Provide and manage skips, enforce differentiated sorting, treat non-routine waste, asbestos, etc. * Control tasks to ensure that the instructions are followed (e.g. "no burning of materials on site"). * Ensure what can be done in a given context and then communicate appropriately with the team to enforce the rule. * Identify what needs to be treated and determine how to do it (see QSE standards - quality, health and environment). Activity 2.7. Permanent quality control of the renovation sites: quality of the execution phases and quality of the finished products. Responsibilities * Permanent verification of the achievements as they are made, with a control sheet for a regular quality follow-up. Tasks * In renovation, the site manager checks more carefully the compatibility of the materials to be applied with the old materials (already applied). * Check for leakage issues, etc. * Check the quality of the treatment of buildings divided into different lots whose construction is spread over many years, where each lot is different, with particular constraints for renovation (different ageing, different technical characteristics, different cloins, etc.) - the rendering of the work is difficult to predict. Activity 2.8. Administrative, financial and legal management of a renovation project Responsibilities * Mastering construction law * Staying within budget * Monitor and regulate the financial aspects through the management of materials and working hours. Tasks * Administrative reporting and site management. * Budget management and monitoring of indicators, including "dry" purchases, drawing up an estimate. * Re-education of all the administrative documents to be used and updated. * Control and alert in case of default. It is not dedicated to financial negotiation. * Filling in specific declarations for the thermal regulation in renovation (RT2021) - consumption to be identified (coefficients to be reached lot by lot). Phase 3: Acceptance of a renovation site and quality control of the work RESPONSIBILITY: shared 50/50 with the works manager on large renovation projects, 100% on small projects (especially in private homes) * he is responsible for the successful completion of the work * it participates in the formalization of reservations AUTONOMY: * this is done in pairs with the works manager, in consultation with the company manager and the architect (depending on the nature of the work and the size of the site) * REPORTING to his hierarchy Activity 3.1. Quality control of final productions Responsibilities * Responsibility for the process and for explaining the malfunctions observed on the site concerned. * Make a link with the initial specifications (compliant/non-compliant). Responsibility to justify deviations. * Anticipation of customer satisfaction. The expectation described in the initial document must always be kept in mind. Tasks within the framework of the OPR procedures (operation prior to acceptance) * Special control of water supply networks, heating, air conditioning, boilers, when the networks have been modified (this is not clipped, unlike new networks) * Check the new balances (beams in relation to the walls, adjustments to ensure the new water flows, networks and electrical power, etc.) * Check whether the new installations are hidden as planned (e.g. need for false ceilings). * A very thorough check of the commissioning. The site manager must reconcile self-confidence and humility. His adaptability and his technical knowledge are essential assets. He must be ingenious. Capitalizing on experience and increasing the skills of the teams (identification of the right contacts at the various service providers or operators in particular. The first quality: you must be rigorous. Make a link with the permanent self-checking. Knowing how to express reservations in relation to the various trades. * Know how to respond positively to external criticism (customers, management, partners) and take it into account. * Negotiate reservations and how to remove them. No particular solution or proposal with regard to the mental load at this stage. Abilities: in digital the site manager must be able to use, read and exploit digital documents and reading tools. (BIM) He must master the basic office automation and syntax. Company image Checking the functionality of the retained heating appliances after intervention. An installation that worked well initially may not work properly after the intervention (electricity, heating, ventilation, etc.). Carry out a commissioning . this check can be devolved to the relevant team leader. "Pre-acceptance operations (in the presence of of the project manager) The project manager is often very concerned about the state of the elements already on the site (well protected and not damaged parquet, cracks, splinters, etc.). In training, it is important to make the students aware of the consequences and responsibilities to which the site manager is exposed in the event of poor reception of the site. The same as in phase 2. The same as in phase 2. The same as in phase 2. The same as in phase 2. The same as in phase 2. Activity 3.2. Operation of acceptance of the work by the customer Responsibilities On major renovation projects, the works manager is responsible for this. On smaller sites, especially for private individuals, it is mainly the site managers who are responsible for this. Tasks * Checking whether anything has been damaged during the work (cornices on the ceiling, parquet, etc.) at the client's and in the neighbourhood - proposing repair work if anything has been damaged. * Follow the highly codified reception procedures. * Identify any rework, hidden defects, etc. and plan additional work that will lead to the lifting of reservations. Activity 3.3. Evaluation of the work carried out, including valorisation and ways of improvement of the team. Responsibilities *
Activity 2.2. Elaboration and implementation of procedures for the proper execution of operations (e.g.: adaptation to site constraints, verification and monitoring of material supplies, verification of delivery times, consideration of energy efficiency, etc.) | Responsibilities * The team leader warns and the site manager finds solutions (e.g. an apparently healthy wall turns out to be rotten when opened: what to do, especially when the surface is large?) * Manage day-to-day contact with clients (it is important to explain to the client what each change to the original plan entails). Tasks * Maintain a more personal relationship with the customer, taking into account his sensitivities, his constraints and his emotional side (the site manager is the privileged interlocutor of the customer) to remain credible and legitimated in front of the customer (crucial aspect for the good progress of a renovation site) * Adapt to site constraints by organizing team activities. * Follow up on the daily supply of materials and ensure that delivery deadlines are met. * Take into account energy efficiency, circular economy, health and safety on site in the balancing and communication of procedures. * Provide for budgetary adjustment possibilities
Activity 2.3. Management of teams on renovation sites (own teams, in cooperation, subcontractors, etc.): monitoring of tasks and anticipation of complex and conflicting situations. Management and monitoring of the work process of the teams, including monitoring and updating of the work schedule, co-activity on site, etc. | Responsibility This activity is the most sensitive: as soon as you get involved with people, it's complex (you have to choose your team leaders well, to get along with them): * Adopt the posture of manager (absolutely fundamental responsibility during this key activity), by controlling the organization of the site. * To avoid the bad management of the renovation site (the slippages are much easier than on the new sites) to avoid conflicts (open or latent within the teams of which the customers can be aware and which harm in the long run the site and the company). * The site manager has the power to "plant" the site, especially if he is not present on the site. Tasks * Recruiting your teams. * Organize the increasingly complex co-activity. * Convey relevant messages to teams (instructions and explanations), paying attention to language and map reading barriers to adapt to varied and diverse audiences. * Carefully craft messages for clients, taking into account their diversity and sensitivity, by activating communication skills. * Informing the teams about safety prevention and passing on instructions to respect the rules, by activating its communication skills and using media adapted to the specificities of renovation sites. * Give the teams the necessary means to carry out what is required. Explain why the means are sometimes lacking, even if the work must be done in spite of everything. * Being often on the ground - this is imperative for renovation sites, the team must feel that he is present, in support of the team leaders who cannot do everything, so he must be present to assist the teams, be able to protect them if necessary, and stand by them in front of the client. * Organize the different interventions well (e.g. the one who has the crane, has the power).
Activity 2.4. Monitoring of relations with the client, the project manager, the architect, the design office, the HSC (health and safety coordinator). | Responsibilities * Adjust the organization of the site and the achievements to the constraints of renovation which one discovers as one goes along (including supplies, subcontracting, etc.), by negotiating with the appropriate interlocutors. * Measure the risk, be tough if you have to (especially important when dealing with safety - if workers don't want to put up a scaffold to save half a day, be assertive about not making them work on a ladder where a scaffold is needed). * Adapting the posture and the discourse to each interlocutor (one adapts a different discourse and a different attitude with an architect (the exchanges are more technical and descending with the architect, there are no relational/motivational stakes, one adapts a posture of the one who is accountable, whereas with the worker, one is a manager). Tasks * Managing surprises and convincing your interlocutors to accept changes within the budget, making them understand that not everything can be planned in advance (e.g. pipes to be adjusted, resizing of foundations, etc.) * Negotiate with partners outside the hierarchy (this is learned in an empirical way, so not learning the law or the rule, but its concrete application in a situation on site, the examples are taken from experience on site, based on these abilities of being a graduate) * Managing complex relationships with architects, especially when it is necessary to negotiate adjustments imposed by the complexity of renovation projects, which are by definition atypical (there must be a partnership with the architect).
Activity 2.5. Organization and control of on-site protection, including assembling/disassembling of scaffolding, work at heights, difficult access, use of hazardous products on renovation sites, etc. | Responsibilities Knowing how to make trade-offs: taking into account the cost of different solutions, safety issues, knowing how to measure and assume the risks, in consultation with the team (Safety guides the choice: if several choices are possible, it is the cost factor that will determine the choice). * To know the legislation related to the rules of protection, safety and health, to know the procedures to follow * Identify different types of risks, such as chemical risks * Identify means of access and circulation * Impose choices and trade-offs Tasks * Regular site visits to keep track of the entire renovation project. * Negotiate and use situational intelligence to avoid being a prisoner of norms, while respecting them. * Impose safety, while respecting the existing building ("in the new building, there are habits that cannot be applied in the renovation") * Finding non-standard solutions for non-standard work situations, e.g. finding special scaffolding, mobile cranes, narrow excavators, etc. These solutions have an additional cost, you have to anticipate (performance with experience).
Activity 2.6. Management of waste treatment in renovation sites: planning and management of waste bins, sorting and recycling operations. | Responsibilities * The site manager must be able to treat ALL types of waste including unforeseen ones such as asbestos, lead or other (regulations and treatment techniques to be known and respected) * The site manager is responsible for setting up the skips, supplies, various evacuations and the protections to be implemented. Tasks * Provide and manage skips, enforce differentiated sorting, treat non-routine waste, asbestos, etc. * Control tasks to ensure that the instructions are followed (e.g. "no burning of materials on site"). * Ensure what can be done in a given context and then communicate appropriately with the team to enforce the rule. * Identify what needs to be treated and determine how to do it (see QSE standards - quality, health and environment).
Activity 2.7. Continuous quality control of renovations sites: quality of construction phases and quality of finished products. | Responsibilities * Permanent verification of the achievements as they are made, with a control sheet for a regular quality follow-up. Tasks * In renovation, the site manager checks more carefully the compatibility of the materials to be applied with the old materials (already applied). * Check for leakage issues, etc. * Check the quality of the treatment of buildings divided into different lots whose construction is spread over many years, where each lot is different, with particular constraints for renovation (different ageing, different technical characteristics, different cloins, etc.) - the rendering of the work is difficult to predict.
Activity 2.8. Administrative, financial and legal management of a renovation site. | Responsibilities * Mastering construction law * Staying within budget * Monitor and regulate the financial aspects through the management of materials and working hours. Tasks * Administrative reporting and site management. * Budget management and monitoring of indicators, including "dry" purchases, drawing up an estimate. * Re-education of all the administrative documents to be used and updated. * Control and alert in case of default. It is not dedicated to financial negotiation. * Filling in specific declarations for the thermal regulation in renovation (RT2021) - consumption to be identified (coefficients to be reached lot by lot).
Phase 3: Acceptance of a renovation site and quality control of the work RESPONSIBILITY: shared 50/50 with the works manager on large renovation projects, 100% on small projects (especially in private homes) * he is responsible for the successful completion of the work * it participates in the formalization of reservations AUTONOMY: * this is done in pairs with the works manager, in consultation with the company manager and the architect (depending on the nature of the work and the size of the site) * REPORTING to his hierarchy
Activity 3.1. Final Production Quality Control | Responsibilities * Responsibility for the process and for explaining the malfunctions observed on the site concerned. * Make a link with the initial specifications (compliant/non-compliant). Responsibility to justify deviations. * Anticipation of customer satisfaction. The expectation described in the initial document must always be kept in mind. Tasks within the framework of the OPR procedures (operation prior to acceptance) * Special control of water supply networks, heating, air conditioning, boilers, when the networks have been modified (this is not clipped, unlike new networks) * Check the new balances (beams in relation to the walls, adjustments to ensure the new water flows, networks and electrical power, etc.) * Check whether the new installations are hidden as planned (e.g. need for false ceilings). * A very thorough check of the commissioning. | The site manager must reconcile self-confidence and humility. His adaptability and his technical knowledge are essential assets. He must be ingenious. | Capitalizing on experience and increasing the skills of the teams (identification of the right contacts at the various service providers or operators in particular. The first quality: you must be rigorous. Make a link with the permanent self-checking. Knowing how to express reservations in relation to the various trades. | * Know how to respond positively to external criticism (customers, management, partners) and take it into account. * Negotiate reservations and how to remove them. | No particular solution or proposal with regard to the mental load at this stage. | Abilities: in digital the site manager must be able to use, read and exploit digital documents and reading tools. (BIM) He must master the basic office automation and syntax. Company image | Checking the functionality of the retained heating appliances after intervention. An installation that worked well initially may not work properly after the intervention (electricity, heating, ventilation, etc.). Carry out a commissioning . this check can be devolved to the relevant team leader. "Pre-acceptance operations (in the presence of of the project manager) The project manager is often very concerned about the state of the elements already on the site (well protected and not damaged parquet, cracks, splinters, etc.). In training, it is important to make the students aware of the consequences and responsibilities to which the site manager is exposed in the event of poor reception of the site. | The same as in phase 2. | The same as in phase 2. | The same as in phase 2. | The same as in phase 2. | The same as in phase 2.
Activity 3.2. Getting Client Agreement/Approval over the work done | Responsibilities On major renovation projects, the works manager is responsible for this. On smaller sites, especially for private individuals, it is mainly the site managers who are responsible for this. Tasks * Checking whether anything has been damaged during the work (cornices on the ceiling, parquet, etc.) at the client's and in the neighbourhood - proposing repair work if anything has been damaged. * Follow the highly codified reception procedures. * Identify any rework, hidden defects, etc. and plan additional work that will lead to the lifting of reservations.
Activity 3.3. Evaluation of the work process, including evaluation, valorising and improvement of the team. | Responsibilities * Preparation of the summary notes at the end of the work, also taking into consideration the problems and points of view of the various parties. * Gap analysis and clarification. * Valuation of positive points, evaluation of processes. Tasks * Analysis of schedules, delays: why are there differences? We go back over our mistakes, we start a dialogue. We build a closeness. * An informal meeting (barbecue, etc.) at the end of the work (especially if it has lasted a long time) is important for team cohesion. * A project to increase the skills of the teams.
Skills and Knowledge
Professional Activities

## Grid 2 Team Leader (EN)
IO1-A3a - Grid 2: Professional Activities and Associated Skills & Knowledge for Building Renovation Team Leaders
|  | Ability to analyse and assess problems, project, anticipate and adapt to complex situations, also taking into account on-site co-activity. | Internal communication capabilities on site and within the company, including the search for alternative solutions in complex situations. Ability to use appropriate communication tools. | Capabilities of communication with external partners (clients, subcontractors, suppliers, etc.). Ability to use appropriate communication and monitoring tools. | Ability to mentally manage workload, including management of stress and job strain. | Ability to use software tools to analyse, evaluate and anticipate. | Knowledge of planning, implementing and controlling the quality of production processes at renovation sites, including the organisation and control of supplies. | Knowledge to plan and control the quality of intermediate and final productions. | Knowledge to manage financial issues and the budget allocated to the renovation site. | Knowledge to integrate an update to the energy standards of buildings during their renovation and to use the appropriate control tools. | Knowledge to integrate the circular economy on renovation sites and to use the appropriate control tools. | Knowledge to integrate occupational health and safety prevention into renovation sites and to use appropriate control tools.
Phase 1: Preparation of a renovation site (the focus should be on this type of site): the team leader does not make any preparations He will only have to prepare his task, he will have an installation plan (on a small site, there are site managers) the team leader works with the workers, while the site manager is in the office. It is a function more vague than that of site manager, but a function nevertheless (training: Professional title of team leader, after BP, level 4
Activity 1.1. Renovation Site Analysis | Responsibilities * In principle, the team leader does not intervene in this phase if the site manager does. Tasks * Decode the plans, use the operating procedures prepared by the site manager | Little or no action in this Phase 1, it can possibly be consulted by the site manager for opinion or advice. Specificity: the adaptation to the existing which characterizes the renovation sites and the diagnosis. * It is more complicated in renovation, it is necessary to foresee many more things (arrival of water points, how I evacuate the dumpsters, the rubble, what is the width of the access road, availability of electrical cables, etc.) * It must think about the realization of the works and their feasibility and all the surroundings. The accesses, the available space, the available height. * Knowing how to read and analyze written material, identifying the delicate points (tensions, difficulties, risks concerning his team). | * Understand the site installation plan - also a communication document (consultable by all participants on site) * Another dynamic Autocad document, - a tool to be inserted in the co-activity on site * Build communication tools to convey safety messages: ratio activities - risks. | * To feel and make feel the wish and desire of the client, of the project. • Get a good feel for the customer's need (the the building, it carries values and it carries human activities, not to betray the will of the customer, to explain him the constraints which limit his wishes. | * Be organized and know your own operation) * Establish support groups of site managers * Learn to consider the unexpected as a sustainable component * Have a balanced professional life * Consider internships with occupational psychologists who would analyze stressful work situations. | * Know how to use tablets, laptops, etc. equipped with applications appropriate to communicate with the hierarchy, with his teams, with customers, etc. | * Decode the plans, use the operating procedures prepared by the site manager * Knowing how to determine the needs in quantity of materials and human resources. But it is not financially responsible. | * Building permit or declaration of works (legislative aspects) * PSMV (plan de sauvegarde et de mise en valeur) to be consulted and any other regulation in relation to classified or unclassified heritage sites. | * General knowledge of specific regulations in terms of energy impact (RT 2020 etc ...) Specific VAT, premiums and subsidies to advise the owner of work. | * General knowledge of what is deductible from VAT, taxes, interest-free loans (the site manager has an obligation to advise, participate in commercial negotiations - the various tax reductions that can encourage customers to do renovation) * Know the limits (what can be renovated and what cannot be renovated by your team). | * Know how to schedule waste sorting. * Knowing how to deal with common and non-common waste, asbestos, etc. * Waste separation and energy saving (e.g. water fountains) - again, a matter of communication with the teams; skips are a cost. | * Knowing in depth the safety regulations (drilling in the joints and not in the stone); the safety net etc... These are more adaptations to be found than compromises. * Enforce safety regulations, show the benefits in concrete terms.
Activity 1.2. Site visit of the future renovation site | Responsibilities * In principle, the team leader does not intervene in this phase if the site manager does. Tasks * Decode the plans, use the operating procedures prepared by the site manager
Activity 1.3. Diagnosis of the existing building prior to intervention | Responsibilities * The team leader may be involved in this activity (not systematically) Tasks * Assist the site manager if necessary.
Activity 1.4. Preparation of the renovation site plan and its layout (tracing, fencing and preparation of the site area) | Responsibilities * The team leader may be involved in this activity (not systematically) Tasks * Assist the site manager if necessary.
Activity 1.5.Planning and phases of the team's work | Responsibilities * Instead, it manages the implementation of the renovation site, the signage and the related logistics Tasks * He organizes his teams. * It manages the stcks of the materials at least one week ahead * He reads and uses the documents produced by the design office or the site manager.
Phase 2: Management of a renovation site. He is manager of his team on a first level, and at the same time semi-executive / semi-manager (profile: levels 3 and 4 plus years of experience)
Activity 2.1. Team briefing / debriefing (daily and periodic) | Responsibilities * He does this when there is no site manager, otherwise not. Tasks * He organizes briefings/debriefings with his team. * He reports daily to the site manager. | * You can't become a team leader without experience. You need knowledge, but above all experience. It is above all chief/neighbourhood manager. * Ability to assess work situations and decide whether to alert the site manager. * Anticipation skills * Be able to plan your team over the week and quantify the materials you will need over the same period. -Their professional identity is first and foremost While technical, they must learn cross-cutting skills. Their technical skills are equivalent to those of a site manager (reading plans, taking measurements, measuring quantities, checking the quality of their team's work). * Power to act in unpredictable situations, to manage the unexpected. | * Ability to ensure the motivation of his team. * To combine his very advanced technical skills with his interpersonal skills, plus his communication skills with the team. * Disseminate the right information to the teams. * On small sites, the two functions are merged. It will to be called "team leader". * Know how to communicate rotation plans. * Know how to communicate with people on site (colour codes, languages, etc.) * Conveying messages to your team, giving instructions, choosing the right means, making sure they understand; giving instructions that are understood by everyone, keeping communication simple, knowing how to decode and construct your message. * Broadcasting: make sure that the instructions are well understood (e.g. 1/4 h safety). * Build ways to communicate safety messages: ratio activities - risks. | * The ability to behave is very important because he is likely to be in contact with customers very frequently (more often on renovation sites than on new construction sites). -fSavoir-être, because it is all the time at the customer's premises. * The management of the occupants of a building site is a specific capacity for renovation sites. | As soon as you get into the human side of things, it's complex (you have to choose your team leaders well, to get on well with them). The team leader must be able to protect the workers, to be in solidarity with them in front of the customer, in front of the site manager, etc. * Knowing how to bring care to the work (fully responsible). | • Know how to use tablets, laptops, etc. equipped with applications appropriate to communicate with the hierarchy, with his teams, with customers, etc. • The team leader is accountable for the task, also with modern communication means (mobile phone, etc.) / use of digital tools even more important for the leader for the team leader than for the site manage | * Compatibility between existing and new materials must be taken into account Beware of the phenomenon of the semi-load-bearing wall (initial partition which over time becomes a load-bearing or stabilising element in the building) In training it is necessary to train to this approach of "surprise" to solve. • Control of the works (including self-checks, on his own initiative), based on the plans. He redoes the spot checks, during the course of the work. There may be Self-checking (designed either by works managers or by site managers). | Building permit or declaration of works (legislative aspects) PSMV (plan de sauvegarde et de mise en valeur) to be consulted and any other regulation in relation to classified or unclassified heritage sites. | * The team leader talks in quantity, not money. * Be sensitive to the cost of materials and operations, such as the cost of a bad sorting (if it is badly sorted, it is not the same cost of treatment: it goes from 20 € to 120 € per ton) | * Rudimentary knowledge of what is deductible from VAT, taxes, interest-free loans - to discuss with customers - the various tax breaks that can encourage customers to do renovation) ;* Know the limits (what can and cannot be renovated within the scope of your activities) | * Know how to sort the waste for which he is fully responsible. * Waste separation and energy saving (e.g. water fountains) - again, a matter of communication with the teams; skips are a cost. | * It is difficult to integrate safety requirements in renovation (unlike in new construction). * Knowledge of gestures and postures to preserve health. * Knowing how to identify all kinds of risks, some of which are more specific to renovation sites: risk of falling rocks, risk of working at height, lead poisoning and asbestos. * Enforce compliance with safety regulations, don't just talk about safety in terms of costs. It is also an investment. A change in mentality is necessary. Show the benefits in concrete terms.
Activity 2.2. Elaboration and implementation of procedures for the proper execution of operations (e.g.: adaptation to site constraints, verification and monitoring of material supplies, verification of delivery times, consideration of energy efficiency, etc.) | Responsibilities * The team leader alerts the site manager so that he can find solutions (e.g. an apparently healthy wall turns out to be rotten when it is opened: what can be done, especially when the surface is large? - You have to explain to the customer what this means). * He/she is the proposer, but not the decision-maker (he/she respects the authority). Tasks * Pass on the right information about the rules to be followed * Plan your week and anticipate the activities of your team. * Prepare daily reports * Contribute to the improvement of operating procedures as a stakeholder * Determine the need for materials, human resources, etc. He's talking quantity, not money. * Control the quality of the executions, step by step
Activity 2.3. Management of teams on renovation sites (own teams, in cooperation, subcontractors, etc.): monitoring of tasks and anticipation of complex and conflicting situations. Management and monitoring of the work process of the teams, including monitoring and updating of the work schedule, co-activity on site, etc. | Responsibilities * Management is limited to his own position and his own team. Tasks * The tasks that make up this activity are the most sensitive, as they are complex, involving humans. * Choose your team well, get along well with them. * Protecting the workers, showing solidarity with them in front of the customer, the site manager, etc. * Listen and anticipate. * He reports any relationship or behavioural problems to the site manager. * Identify all kinds of risks, some of which are more specific to renovation sites: risk of falling rocks, risk of working at height, lead and asbestos poisoning.
Activity 2.4. Monitoring of relations with the client, the project manager, the architect, the design office, the HSC (health and safety coordinator). | Responsibilities * The team leader is not usually in contact with external partners, including customers. * On the other hand, he will be in contact with the occupant (but if there are problems, the site manager will intervene). * Be able to build confidence. Tasks * At least make your team aware of the rules of good manners, coupled with the rules of know-how (e.g. lifting the furniture instead of pushing it).
Activity 2.5. Organization and control of on-site protection, including assembling/disassembling of scaffolding, work at heights, difficult access, use of hazardous products on renovation sites, etc. | Responsibilities * The team leader is responsible for safety prevention in his team, under the supervision of the site manager. * Use technical and regulatory skills in this area. Tasks * Plan his week at this level and anticipate the assembly and disassembly of scaffolding or other equipment necessary for the smooth running of the site. * Formulate proposals to find solutions to problems that arise in terms of security or to anticipate their arrival. * Pass on the right information about the rules to be followed * Ensure compliance with safety rules, aloccol on site (during breaks) - risk situations (e.g. risks of falling rocks, falls from height, poisoning by asbestos, lead, sharp hyoer glazing, non-standard installations in places that are difficult to access, removal of rubble without a lift, in a courtyard where the lorry did not pass). * Monitor gestures and postures.
Activity 2.6. Management of waste treatment in renovation sites: planning and management of waste bins, sorting and recycling operations. | Responsibilities * Use technical and regulatory skills in this area. Tasks * The team leader has to control the sorting of the waste in the three skips (if it is badly sorted, it is not the same cost of treatment: it goes from 20 € to 120 € the ton) * Pass on the right information about the rules to be followed
Activity 2.7. Continuous quality control of renovations sites: quality of construction phases and quality of finished products. | Responsibilities * It is the team leader who ensures the permanent control of the work, step by step. Tasks * Make sure that the materials to be applied are compatible with the old materials (already applied). * Check for leakage issues, etc. * Check the quality of the treatment of buildings divided into different lots whose construction is spread over many years, where each lot is different, with particular constraints for renovation (different ageing, different technical characteristics, different cloins, etc.) - the rendering of the work is difficult to predict.
Activity 2.8. Administrative, financial and legal management of a renovation site. | Responsibilities * The team leader may be involved in this activity (not systematically) Tasks * Assist the site manager if necessary.
Phase 3: Acceptance of a renovation site and quality control of the work
Activity 3.1. Final Production Quality Control | Responsibilities * The team leader may be involved in this activity (not systematically), but it is mainly the responsibilities of the site manager. Tasks * Assist the site manager if necessary. | The team leader must reconcile self-confidence and humility adapted to his professional context. His adaptability and technical knowledge are essential assets. He must be the technical specialist recognized by the workers and by the site manager. | Capitalizing on experience and increasing the competence of teams. Knowing how to evaluate and express reservations in relation to the different workers, procedures and organization modes. | * Know how to respond positively to external criticism (mainly from customers, management, partners) and take it into account. * Negotiate the way to remove reservations. | The same as in phase 2, but with a much smaller spectrum of use. | The same as in phase 2, but with a much smaller spectrum of use. | The same as in phase 2, but with a much smaller spectrum of use. | The same as in phase 2, but with a much smaller spectrum of use. | The same as in phase 2, but with a much smaller spectrum of use. | The same as in phase 2, but with a much smaller spectrum of use. | The same as in phase 2, but with a much smaller spectrum of use. | The same as in phase 2, but with a much smaller spectrum of use.
Activity 3.2. Getting Client Agreement/Approval over the work done | Responsibilities * Team leaders may participate in the acceptance of sites (depending on the size of the site). Tasks * Detail what needs to be taken back and how.
Activity 3.3. Evaluation of the work process, including evaluation, valorsing and improvement of the team. | Responsibilities * Team leaders participate in this phase as spokespersons for their teams. Tasks * They give their opinion on what worked and what didn't work on the renovation site. * They participate in the formulation of proposals to improve the functioning (organizations and people).
Skills and Knowledge
Professional Activities

## Glossary (FR&EN)
IO1-A3a - RenovUp - Glossaire / Glossary
| FR | EN
Compétence (gén.) / Competence (gen.) | La capacité à mettre en œuvre des résultats/acquis d'apprentissage d'une manière appropriée dans un contexte défini (éducation, travail, développement personnel ou professionnel), c'est-à- dire à appliquer des savoirs et des aptitudes de manière autonome et responsable | The ability to apply learning outcomes adequately in a defined context (education, work, personal or professional development), that is to apply knowledge and aptitudes in an autonomous and responsible manner.
Compétence concernant les chefs d'équipe/ Competence concerning team leaders | Gérer soi-même son travail dans la limite de consignes de travail généralement prévisibles mais susceptibles de changer. Superviser le travail habituel d’autres personnes, en assumant certaines responsabilités en matière d’évaluation et d’amélioration des activités liées au travail sur le chantier concerné. Intégrer l'imprévu dans l'organisation et la mise en oeuvre de ses activités. | Manages his/her own work within generally predictable but changing work instructions. Supervises the routine work of others, with some responsibility for evaluating and improving work-related activities on the renovation worksite. Integrates the unexpected into the organization and implementation of activities.
Compétence concernant les chefs de chantier de rénovation / Competence concerning renovation worksite managers | Gérer et superviser des activités dans un contexte de travail sur chantier de rénovation où les changements sont en général imprévisibles. Examiner et améliorer ses résultats et ceux des autres grâce à une gestion et à des négociations adéquates (avec l'équipe sur chantier et avec tous les autres partenaires). | Manages and supervises activities on a renovation site within a context where changes are usually unpredictable. Reviews and improves his/her own and others' performance through proper management and negotiation (with the site team and all other partners).
Capacités / Capabilities | Prédispositions à réaliser des activités et des tâches qui impliquent la nécessité de faire face à des situations de travail où il faut résoudre des problèmes (trouver des solutions adéquates). Les capacités sont basées sur la maîtrise des savoirs (théoriques et/ou factuels) et sur les aptitudes cognitives (fondées sur l’utilisation de la pensée logique, intuitive et créative) et pratiques (fondées sur la dextérité ainsi que sur l’utilisation de méthodes, de matériels, d’outils et d’instruments). | Predisposition to carry out activities and tasks that involve the need to deal with work situations where problems have to be solved (finding appropriate solutions). Capabilities are based on the mastery of knowledge (theoretical and/or factual) and skills (cognitive: based on the use of logical, intuitive and creative thinking, and practical: based on dexterity as well as on the use of methods, materials, tools and instruments).
Savoirs / Knowledge | Ensemble cohérent de connaissances acquises au contact de la réalité ou par l'étude qui servent, dans notre cas, à exercer les activités sur des chantiers de rénovation des bâtiments. Les savoirs peuvent être théoriques ou factuels. Dans notre cas, les savoirs, associés aux aptitudes, font partie des capacités des chefs d'équipe et des chefs de chantier. | A coherent body of awareness acquired through contact with reality or through study which is used, in our case, to carry out activities on building renovation sites. Knowledge can be theoretical or factual. In our case, knowledge, together with skills, is part of the capabilities of team leaders and site managers.
Aptitudes / Skills | Dispositions de quelqu'un à faire quelque chose (dans notre cas : assumer la fonction de chef d'équipe ou de chef de chantier sur des chantiers de rénovation des bâtiments). Les aptitudes peuvent être cognitives (naturelles) ou pratiques (acquises). Dans notre cas, les aptitudes, associées aux savoirs, font partie des capacités des chefs d'équipe et des chefs de chantier. | A person's willingness to do something (in our case: to act as a team leader or site manager on building renovation sites). Skills can be either cognitive (natural) or practical (acquired). In our case, skills, together with knowledge, are part of the capabilities of team leaders and site managers.
Activité / Activity | Ensemble des actions diverses menées dans un secteur, ou qui se manifestent dans un lieu (ici : sur un chantier de rénovation des bâtiments). | Various actions carried out in a sector, or which take place in a specific situation (here: on a building renovation site).
Tâche / Task | Ouvrage à faire dans un temps déterminé et à certaines conditions, en tant que partie d'une activité. | Work to be done within a certain time and under certain conditions, as part of an activity.
Sources: Cedefop (2006), EQF (2017), Larousse (2021).